UNDOS timelines

|  |  |  |
| --- | --- | --- |
| Date | Activity  | Who |
| ~~Beginning of January~~ | ~~Workshops to facilitate more involvement from Indigenous groups~~ | ~~Molly will host, as DCMR cannot provide toll-free call in~~ |
| ~~January 25.~~ | ~~Preliminary draft submitted to Task force.~~ | ~~DCMR~~ |
| ~~January 26-27.~~ | ~~Quick review of draft (please note this in your calendar)~~ | ~~Task Force members~~ |
| ~~January 28~~~~th~~ | ~~Brief Task Force meeting to address major points (including language)~~ | ~~Task Force members~~ |
| February 28. | Revised draft sent to WG chairs for initial comments (deadline March 5th) | DCMR + WG chairs |
| March 13. | Draft Action plan made available for community review on [oceandecae.dk](http://oceandecae.dk).Organizations representing Indigenous Peoples will be contacted directly. | DCMR |
| March 16. | Online consultation on action plan | DCMR + WG chairs |
| March 28. | Consultation closes and preparations of final versions begins | DCMR |
| April 15 | DCMR submit final draft to Task Force for final round of review. | Task Force members |
| April 25  | Task Force accepts the ‘final Arctic Action v1’  | Task Force members |
| May 1 | Launch of Arctic Action Plan |   |
| May 7-10 | DCMR presents action plan at Arctic Ministerial meeting (Tokyo/online) | DCMR |